## Slide 1
Team Progress Analysis & Work Audit
Institutional ERP System Development (Week 03 / Week 04)
Prepared by: Lakshya Singhal

## Slide 2
Work Analysis Overview — Prashant Jain
Assigned Domain: Academic & Institutional Backend Modules.
Audit Objective: Cross-examine assigned tasks against logged progress in the Developer Diary (dev_diary.md).
Key Summary Findings:
• Execution Alignment: Core assigned modules (Campus, Department, Academic Year) were completed.
• Schedule Shifts: Significant timing differences exist between the task assignment tracker and logged execution.
• Deliverable Deviations: Architectural changes and additional database migrations occurred during Day 01 setup.

## Slide 3
Prashant Jain — Assigned vs. Actual Execution
Day | Assigned Task (Tracker) | Actual Logged Activity (Dev Diary) | Audit / Status
Day 01 | Institution Schema | Architecture Reset & Global Exception Handler | Deviated: Base setup focused; V1 schema added.
Day 02 | Campus Management | Campus CRUD & Migration (V2 SQL) | Completed: Aligned with domain.
Day 03 | Department Management | Department CRUD & Migration (V3 SQL) | Completed: Aligned with domain.
Day 04 | Academic Year | AcademicYear CRUD & Migration (V4 SQL) | Completed: Package naming resolved.
Day 05 | Halt | Semester CRUD & Migration (V5 SQL) | Completed: Executed during planned halt.
Day 06 | Halt | Program & Batch CRUD (V6, V7 SQL) | Completed: Executed during planned halt.

## Slide 4
Prashant Jain — Discrepancies & Work Audit
1. Documentation Reporting vs. Logged Output
The tracking sheet logs 'Delayed' for documentation across Days 02–04, whereas dev_diary.md contains detailed package mappings, problem statements, and solutions.
2. Code Submission Status on Day 01
Tracker marks Day 01 Code Submission as 'null', but the Developer Diary documents a full architecture reset, monorepo backend creation, and GlobalExceptionHandler setup.
3. Schedule & Phase Misalignment
The task breakdown assigns Semester, Program, Course, and Curriculum to Week 04. However, dev_diary.md records Semester, Program, and Batch as completed in Days 05–06 of Week 03.

## Slide 5
My Work & Deliverables — Lakshya Singhal
Core Architectural Achievements (Days 01 – 06):
• Enterprise Foundation: Built a complete frontend architecture using React 19, TypeScript 5.9, Vite 5, and Tailwind CSS 3.4.
• Codebase Volume: Engineered 140 fully implemented source files containing 9,763 lines of clean TypeScript code.
• Verified Build Quality: Production build (npm run build) completed with Exit Code 0 across 2,755 transformed modules and 0 compiler errors.

## Slide 6
Lakshya Singhal — System Architecture & Components
• Design System & Layout Shell: Implemented AppLayout, Sidebar, Topbar, design tokens (colors, typography), and Cmd+K Global Search modal.
• Centralized API & Interceptor Hub: Axios client with JWT bearer injection, correlation IDs, status error mapping (200-504), and a 401 silent token refresh queue to handle race conditions.
• Enterprise Form & Validation Engine: React Hook Form + Zod validation, dependent select fields, autosave, dirty state tracking, and normalized error formatters.

## Slide 7
Lakshya Singhal — Week 03 / Week 04 Plan
Day 01 — Advanced Data Management: API client abstractions, loading/error states, and server-side table hook (useServerTable).
Day 02 — Frontend-Backend Integration: Direct Spring Boot REST API integration, environment configuration, and token handling.
Day 03 — Student Module UI: Complete UI screens for Student Dashboard, Student CRUD, and Student Status lifecycle.
Day 04 — Institution Module UI: Management UI for Institution, Campus, and Department entries.
Day 05–06 — Reusable Forms & DataTables: Dynamic field validation, server-side pagination, multi-column sorting, and instant CSV exports.

## Slide 8
Summary & Project Readiness
Audit Summary: Prashant Jain completed key backend domain modules[cite: 5], though timing and documentation entries showed variations between tracking logs[cite: 8] and Developer Diary entries[cite: 5].
Frontend Readiness: Core frontend architecture (Lakshya Singhal) is 100% built, compiled with zero errors, and ready for full REST API integration[cite: 7].
Next Steps: Connect Spring Boot services to frontend API client hooks and execute full end-to-end integration testing[cite: 6, 7].